| TASK | OWNER | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Kick-Off Meeting | All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create Course Project Plan | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Course Project Plan | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STORYBOARDING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Storyboard 1st Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Storyboard 1st Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Storyboard 2nd Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Storyboard 2nd Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROTOTYPE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prototype 1st Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Prototype 1st Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Course 1st Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Course 1st Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Course 2nd Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Course 2nd Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Course Final Draft | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approve Course Final Draft | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TESTING & QA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test Course | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Make Final Course Edits | Developer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COURSE DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publish to LMS | LMS Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communicate Course Availability | SME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |